## SEP-2020
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## OCT-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 01/10/2020 | QMVAR | Activity Report & PL Tracking Sheet | Gathering Req | Completed
2 | 02/10/2020 | QMVAR | Activity Report-sony | Analsyse-20% | InProgress
3 | 03/10/2020 | WeekEnd
4 | 04/10/2020 | WeekEnd
5 | 05/10/2020 | QMVAR | Activity Report-sony, Hayaai-Insert Rst Code columns and datas | Hayaai-100%,AR Analyse-10% | Hayaii-completed,AR-Inprogress
6 | 06/10/2020 | QMVAR | Activity Report-sony | Analyse-100% | Completed
7 | 07/10/2020 | QMVAR | Activity Report-sony-creating tables and start design | 10% | InProgress
8 | 08/10/2020 | QMVAR | Activity Report-sony- start design & coding | 20% | InProgress
9 | 09/10/2020 | QMVAR | Activity Report-sony-implementing coding | 40% | InProgress
10 | 10/10/2020 | WeekEnd
11 | 11/10/2020 | WeekEnd
12 | 12/10/2020 | QMVAR | Activity Report-sony-implementing coding-Hataai datas insertion-Query issue | Query issue-100%Implemention-50% | InProgress
13 | 13/10/2020 | QMVAR | Activity Report-sony-implementing coding | 60% | InProgress
14 | 14/10/2020 | QMVAR | Activity Report-sony-implementing coding | 80% | InProgress
15 | 15/10/2020 | QMVAR | Activity Report-sony-implementing coding | 90% | InProgress
16 | 16/10/2020 | QMVAR | Activity Report-sony-implementing coding and checking results | 95% | InProgress
17 | 17/10/2020 | WeekEnd
18 | 18/10/2020 | WeekEnd
19 | 19/10/2020 | QMVAR | Activity Report-sony-code verification |  | InProgress
20 | 20/10/2020 | QMVAR | Activity Report-sony-testing and code results |  | InProgress
21 | 21/10/2020 | QMVAR | Activity Report-sony | 100% | Completed
22 | 22/10/2020 | QMVAR | SID PL Tracking-Gathering Req | 10% | InProgress
23 | 23/10/2020 | QMVAR | SID PL Tracking-Analyse | 30% | InProgress
24 | 24/10/2020 | QMVAR | SID PL Tracking-Design Added | 40% | InProgress
25 | 25/10/2020 | WeekEnd
26 | 26/10/2020 | Pooja Holidays
27 | 27/10/2020 | QMVAR | SID PL Tracking-Tables Added | 50% | InProgress
28 | 28/10/2020 | QMVAR | SID PL Tracking-Implemention code | 60% | InProgress
29 | 29/10/2020 | QMVAR | SID PL Tracking-Verficaton code | 70% | InProgress
30 | 30/10/2020 | QMVAR | SID PL Tracking-Testing code and Results | 80% | InProgress
31 | 31/10/2020 | WeekEnd

## NOV-2020
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## DEC-2020
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold