## SEP-2020
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## OCT-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 01/11/2020 | WeekEnd
2 | 02/11/2020 | QMVAR | SID PL Tracking-Testing code and error fixing | 80%
3 | 03/11/2020 | QMVAR | SID PL Tracking-Testing code and calculation testing
4 | 04/11/2020 | QMVAR | SID PL Tracking-Testing code and calculation testing
5 | 05/11/2020 | QMVAR | SID PL Tracking-Testing code and Results
6 | 06/11/2020 | QMVAR | SID PL Tracking-Testing code and Results | 100% | Completed
7 | 07/11/2020 | WeekEnd
8 | 08/11/2020 | WeekEnd
9 | 09/11/2020 | NMVAR | Analyse the code and error fixing
10 | 10/11/2020 | NMVAR | Analyse the code and error fixing
11 | 11/11/2020 | NMVAR | Analyse the code and error fixing
12 | 12/11/2020 | NMVAR | Analyse the code and error fixing
13 | 13/11/2020 | NMVAR | Analyse the code and error fixing | 30%
14 | 14/11/2020 | WeekEnd
15 | 15/11/2020 | WeekEnd
16 | 16/11/2020 | Leave | Sick Leave
17 | 17/11/2020 | Leave | Sick Leave
18 | 18/11/2020 | Soniya | Soniya Japanese issue analyse | 50%
19 | 19/11/2020 | Soniya | Soniya Japanese issue analyse and fixed | 100% | Completed
20 | 20/11/2020 | NMVAR | Analyse the code and error fixing
21 | 21/11/2020 | WeekEnd
22 | 22/11/2020 | WeekEnd
23 | 23/11/2020 | NMVAR | Analyse the code and error fixing
24 | 24/11/2020 | NMVAR | Analyse the code and error fixing
25 | 25/11/2020 | NMVAR | Analyse the code and error fixing
26 | 26/11/2020 | NMVAR | Analyse the code and error fixing
27 | 27/11/2020 | NMVAR | Analyse the code and error fixing
28 | 28/11/2020 | NMVAR | Analyse the code and error fixing | 50%
29 | 29/11/2020 | NMVAR | Analyse the code and error fixing
30 | 30/11/2020 | NMVAR | Analyse the code and error fixing |  | Inprogress

## NOV-2020
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## DEC-2020
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold